## Summary
Hollow Visible Entity Asset Inventory
Complete visible-entity asset matrix for players, enemies, items, environmental entities, UI, Room Designer, VFX, and required production assets.
Metric | Value
Visible entity rows | 67
Groups | 7
P0 core entities | 16
P1 high entities | 33
ArtPass prefabs already mapped | Prototype placeholders exist for core runtime roles
Main risk | Most rows still need final mesh/material/texture/VFX art
Group | Entity count | Priority | Entity count
Player | 4 | P0 - Core | 16
Enemy | 9 | P1 - High | 33
Reward / Item | 11 | P2 - Medium | 13
Environment | 15 | P3 - Low | 4
Room Designer | 13 | P3 - Planned | 1
UI / HUD | 7
VFX | 8

## Entity Matrix
Full Visible Entity Matrix
Every currently visible or planned-near-term visible entity that requires art production: mesh, material, texture, VFX, animation, UI/icon, or related presentation assets.
Group | Entity | Runtime Role / ID | Current Source | Required Mesh / 3D Object | Required Materials | Required Textures | Required VFX | Required Animation | Required UI / Icon / Label | Production Notes | Priority | Current Status
Enemy | Normal Chaser | spawnEnemyNormal / EnemyNormal / Chaser | AP_EnemyNormal.prefab + Enemy_Normal.asset | Small grounded enemy mesh | Red/corrupt enemy material | Base color, roughness, optional eye/glow | EnemyHit, EnemyDeath | Idle, chase wobble, hit, death pop | Encounter icon optional | Baseline enemy; silhouette should be simplest. | P0 - Core | Prototype ArtPass placeholder
Enemy | Stone Warden boss | spawnEnemyBoss / EnemyBoss / BossWarden | AP_EnemyBoss.prefab + Enemy_Boss.asset | Large boss silhouette, stone guardian body | Stone, moss/ember cracks, boss accent | Stone normal, crack/emissive mask optional | Charge, projectile burst, EnemyHit, EnemyDeath | Idle, slow pursue, charge windup, low-health burst, death | Boss icon/nameplate later | First boss gatekeeper; strongest silhouette requirement. | P0 - Core | Prototype ArtPass placeholder
Environment | Door active/open | PresentationPrefabRole.DoorActive / MaterialRole.DoorActive | AP_DoorActive.prefab | Door/gate active marker mesh | Active door material | Door rune texture | DoorUnlock | Open/activate pulse | Arrow/door icon optional | Shows connected traversable path. | P0 - Core | Prototype ArtPass placeholder
Environment | Door locked | PresentationPrefabRole.DoorLocked / MaterialRole.DoorLocked | AP_DoorLocked.prefab | Door frame/slab/gate mesh | Locked door material | Lock/rune texture | DoorUnlock | Lock pulse/shake optional | Lock icon optional | Shows traversal blocked during combat or boss-key lock. | P0 - Core | Prototype ArtPass placeholder
Environment | Hub return / boss portal | PresentationPrefabRole.HubReturnPortal / MaterialRole.HubReturnPortal | AP_HubReturnPortal.prefab + HubReturnPortal.prefab | Portal ring/pool/gate mesh | Portal material | Swirl/noise/emissive texture | PortalComplete | Swirl/pulse | Portal label optional | Currently transitions into inter-branch hub after boss. | P0 - Core | Prototype ArtPass placeholder
Environment | Inter-branch hub shop stand | PresentationPrefabRole.HubShop / MaterialRole.HubShop | AP_HubShop.prefab + HubShop.prefab | Shop stand/table/pedestal mesh | Shop wood/stone/cloth material | Shop sign/card texture | Purchase/RewardClaim later | Idle candle/pulse optional | Shop label/card text | Hub shop is player-facing after boss. | P0 - Core | Prototype ArtPass placeholder
Environment | Next branch portal | PresentationPrefabRole.NextBranchPortal / MaterialRole.NextBranchPortal | AP_NextBranchPortal.prefab + NextBranchPortal.prefab | Portal/card/gate mesh for branch choices | Next portal material | Seed/branch rune texture | PortalComplete | Idle swirl/pulse | Portal card text/seed | Must distinguish three next branch choices. | P0 - Core | Prototype ArtPass placeholder
Environment | Rock obstacle block | PresentationPrefabRole.RoomObstacleRock / MaterialRole.RoomObstacleRock | AP_RoomObstacleRock.prefab + runtime obstacle | 1m obstacle mesh, top at 1m, bottom at floor | Rock/stone/block material | Stone albedo/normal/roughness | Projectile hit optional | None or tiny hit shake | None | Must align with gameplay collider; visual bottom at y=0. | P0 - Core | Prototype ArtPass placeholder
Environment | Room floor | PresentationPrefabRole.RoomFloor / MaterialRole.RoomFloor | AP_RoomFloor.prefab + RoomRuntimeRoot floor | Tile/floor slab mesh or modular plane | Dark toy-diorama floor material | Albedo, roughness, normal, grid/wear masks | RoomClear optional | None or subtle material pulse | None | Most visible environment asset; keep readable under combat. | P0 - Core | Prototype ArtPass placeholder
Environment | Shop cards | HubShopCard / HubShopOffer | Runtime UI/card objects | Three card meshes or world-space UI cards | Card normal/affordable/sold materials | Card face/icon textures | Purchase success/fail cue later | Hover/affordable pulse, sold dim | Offer name, price, effect, SOLD/Need souls | Critical for M21 readability; not currently a separate prefab role. | P0 - Core | Prototype ArtPass placeholder
Player | Player character | PresentationPrefabRole.Player / MaterialRole.PlayerBody | AP_Player.prefab + PlayerCharacter.prefab | 1 readable player body mesh; optional head/body split; meter-scale pivot at feet/center | Player body material, accent/emissive soul material | Base color, roughness/normal optional, small accent mask | Player hit cue; optional spawn/respawn cue | Idle breathing/bob, hit flinch, optional run lean | HUD portrait/icon later | Must be unmistakable from enemies in top/3-4 camera. | P0 - Core | Prototype ArtPass placeholder
Player | Player projectile | PresentationPrefabRole.Projectile / MaterialRole.Projectile | AP_Projectile.prefab + ProjectileBase.prefab | Small orb/bolt mesh or billboard | Bright projectile material | Glow/noise texture optional | ProjectileFire, enemy hit impact | Looping spin/trail optional | None | Projectile must remain readable against dark floor. | P0 - Core | Prototype ArtPass placeholder
Reward / Item | Boss key pickup | PresentationPrefabRole.BossKeyPickup / MaterialRole.BossKeyPickup | AP_BossKeyPickup.prefab + BossKeyPickup.prefab | Key/fragment/glyph mesh | Boss key gold/ember material | Key/rune texture optional | RewardClaim or DoorUnlock | Bob, sparkle, claim pop | Boss key HUD icon later | Must communicate boss door unlock clearly. | P0 - Core | Prototype ArtPass placeholder
Reward / Item | Generic room reward pickup | PresentationPrefabRole.RewardPickup / MaterialRole.RewardPickup | AP_RewardPickup.prefab + RoomRewardPickup.prefab | Pickup pedestal/orb/chest-like mesh | Reward glow material | Sparkle/emissive texture optional | RewardClaim | Idle bob, claim pop | Reward message in HUD | Used for standard, treasure, boss rewards unless specialized later. | P0 - Core | Prototype ArtPass placeholder
Room Designer | Designer cursor | MaterialRole.DesignerCursor | Generated cursor cube | Cursor highlight box/ring | Cursor highlight material | None | DesignerPlace/Erase | Cursor pulse optional | Cursor coordinate label | Primary authoring pointer. | P0 - Core | Prototype ArtPass placeholder
UI / HUD | Shop offer text/card UI | HubShopCardViewModel / HubShopCard | Runtime shop cards | World-space card/panel mesh | Affordable/unaffordable/sold materials | Offer icons/card art | Purchase/fail cue later | Affordable pulse, sold dim | Name, price, effect, SOLD/Need souls | Critical for M21 shop clarity. | P0 - Core | Prototype ArtPass placeholder
Enemy | Ash Charger | spawnEnemyCharger / EnemyCharger / Charger | AP_EnemyCharger.prefab + Enemy_Charger.asset | Pointed/forward-leaning charger mesh | Orange ember/charge material | Heat/crack texture optional | Charge windup, EnemyHit, EnemyDeath | Windup, charge burst, recovery | Encounter icon optional | Windup readability is more important than final art. | P1 - High | Prototype ArtPass placeholder
Enemy | Bone Turret | spawnEnemyTurret / EnemyTurret / TurretShooter | AP_EnemyTurret.prefab + Enemy_Turret.asset | Stationary turret/statue/eye mesh | Bone/stone + projectile accent | Bone/stone texture optional | Enemy projectile fire, EnemyHit, EnemyDeath | Aim turn, fire recoil, hit | Encounter icon optional | Must read stationary/ranged. | P1 - High | Prototype ArtPass placeholder
Enemy | Enemy projectile | PresentationPrefabRole.EnemyProjectile / MaterialRole.EnemyProjectile | AP_EnemyProjectile.prefab + EnemyProjectileController | Small hostile bolt/orb mesh | Hostile projectile material distinct from player | Glow/noise texture optional | Projectile fire and player hit | Spin/trail optional | None | Must be distinct from player projectile color/language. | P1 - High | Prototype ArtPass placeholder
Enemy | Flying Chaser | spawnEnemyFlying / EnemyFlying / FlyingChaser | AP_EnemyFlying.prefab + Enemy_Flying.asset | Floating enemy mesh with wings/orb/soul form | Blue/airborne enemy material | Wing/soul texture optional | EnemyHit, EnemyDeath | Hover loop, hit, death | Encounter icon optional | Must read as obstacle-bypassing/flying. | P1 - High | Prototype ArtPass placeholder
Enemy | Husk Splitter | spawnEnemySplitter / EnemySplitter / Splitter | AP_EnemySplitter.prefab + Enemy_Splitter.asset | Fragile pod/husk mesh | Green split/swarm material | Crack/shell texture optional | Split/death burst, EnemyHit | Pulse before split, pop death | Encounter icon optional | Death spawning should be visually obvious. | P1 - High | Prototype ArtPass placeholder
Environment | Door cleared | PresentationPrefabRole.DoorCleared / MaterialRole.DoorCleared | AP_DoorCleared.prefab | Cleared/open door variant | Cleared/greenish material | Glow/rune texture | RoomClear/DoorUnlock | Clear flash optional | None | Post-clear readability. | P1 - High | Prototype ArtPass placeholder
Environment | Door unavailable | PresentationPrefabRole.DoorUnavailable / MaterialRole.DoorUnavailable | AP_DoorUnavailable.prefab | Disabled/decorative door marker | Muted unavailable material | Cracked/blocked texture | None | None | None | Unconnected macro-room ports should read inactive, not broken. | P1 - High | Prototype ArtPass placeholder
Environment | Secret door debug marker | PresentationPrefabRole.SecretDoorDebug / MaterialRole.SecretDoorDebug | AP_SecretDoorDebug.prefab | Secret wall/door marker mesh | Secret door material | Secret glyph texture | DoorUnlock optional | Pulse/hidden reveal optional | Secret icon optional | Currently visible/debug-marked secret; future hidden secret readability. | P1 - High | Prototype ArtPass placeholder
Player | Player hit feedback | VfxCueId.PlayerHit / AudioCueId.PlayerHit | VFX_VfxPlayerHit.prefab | Particle/burst visual | Damage flash material | Hit spark/noise texture optional | PlayerHit | Brief flash/pulse | HP feedback in HUD | Feedback should be visible but not obscure combat. | P1 - High | Prototype ArtPass placeholder
Reward / Item | Boss Sigil | Reward_BossSigil / PassiveItem | Reward pickup generic visual | Large sigil/crest mesh | Boss reward material | Sigil texture/emissive mask | RewardClaim, RoomClear | Hover, pulse, claim burst | Boss reward icon | Boss reward should feel more important than standard pickups. | P1 - High | Prototype ArtPass placeholder
Reward / Item | Heal shop offer | HubShopOffer heal | HubShopCard text/card visual | Card/potion/heal token mesh or UI card face | Healing card material | Heart/potion icon texture | RewardClaim/Shop purchase later | Card pulse on affordable | Shop card text/icon | Needs clear HP restoration identity. | P1 - High | Prototype ArtPass placeholder
Reward / Item | Soul currency pickup/cache | Reward_SoulCache / TreasureCache currency rewards | RewardPickup visual currently reused | Soul orb/cache variant or coin cluster | Soul currency material | Soul swirl/noise optional | RewardClaim | Bob, sparkle | Soul icon for HUD/shop | Needed for currency-only rewards and shop readability. | P1 - High | Prototype ArtPass placeholder
Room Designer | Active door anchor | RoomDesignerDoorKinds.Door / MaterialRole.DesignerDoorActive | Generated port marker | Active door marker | Active door material | Door icon/glyph | DesignerPlace/Erase | Pulse optional | doorAnchorActive label | Exports as runtime door port. | P1 - High | Prototype ArtPass placeholder
Room Designer | Available door anchor | RoomDesignerDoorKinds.Available / MaterialRole.DesignerDoorAvailable | Generated port marker | Door anchor ghost marker | Available anchor material | Port icon/glyph optional | DesignerPlace/Erase | Pulse optional | doorAnchorAvailable label | Pre-available exposed chunk-face port. | P1 - High | Prototype ArtPass placeholder
Room Designer | Designer grid | MaterialRole.DesignerGrid | Generated grid lines | Thin grid line mesh/cubes | Designer grid material | None | Designer place/erase | None | Grid labels optional | Needs high readability in editor/viewport. | P1 - High | Prototype ArtPass placeholder
Room Designer | Designer ground tile | RoomDesignerCellKinds.Ground / MaterialRole.DesignerGround | Generated tile preview | 1m ground block/slab | Designer ground material | Tile texture optional | DesignerPlace/Erase | None | tileGround label | Authoring visualization, not runtime final art. | P1 - High | Prototype ArtPass placeholder
Room Designer | Designer hole tile | RoomDesignerCellKinds.Hole / MaterialRole.DesignerHole | Generated tile preview | Hole/void preview tile | Designer hole material | Void texture optional | DesignerPlace/Erase | None | tileHole label | Should differ clearly from missing/unloaded content. | P1 - High | Prototype ArtPass placeholder
Room Designer | Designer labels / panels | RoomDesignerController HUD | Runtime UI Text | World-space label panels optional | Panel/text materials | Icons for tools/ports later | DesignerPlace/Erase cues | Panel transitions optional | Tool, footprint, validation, controls | Current authoring UI depends on readability. | P1 - High | Prototype ArtPass placeholder
Room Designer | Designer rock tile | RoomDesignerCellKinds.Rock / MaterialRole.DesignerRock | Generated tile preview | 1m rock/block preview | Designer rock material | Rock texture optional | DesignerPlace/Erase | None | tileRock label | Should match runtime obstacle scale. | P1 - High | Prototype ArtPass placeholder
Room Designer | Enemy spawn marker | spawnEnemyNormal/Flying/Fast/Heavy/Charger/Turret/Splitter | Generated marker | Small colored marker/silhouette | Enemy spawn marker materials per variant | Variant icons | DesignerPlace/Erase | Pulse optional | spawn_point_enemy_* labels | Needs variant readability for encounter authoring. | P1 - High | Prototype ArtPass placeholder
Room Designer | Reward spawn marker | spawn_point_roomReward / MaterialRole.DesignerSpawnReward | Generated marker | Reward anchor marker | Reward marker material | Reward icon | DesignerPlace/Erase | Pulse optional | spawn_point_roomReward label | Where room rewards can appear. | P1 - High | Prototype ArtPass placeholder
Room Designer | Safe start marker | spawn_point_safeStart / MaterialRole.DesignerSpawnSafeStart | Generated marker | Safe start marker | Safe marker material | Start icon | DesignerPlace/Erase | Pulse optional | spawn_point_safeStart label | Must be clearly unique. | P1 - High | Prototype ArtPass placeholder
Room Designer | Secret door anchor | RoomDesignerDoorKinds.Secret / MaterialRole.DesignerDoorSecret | Generated port marker | Secret door marker | Secret door material | Secret glyph | DesignerPlace/Erase | Pulse optional | doorAnchorSecret label | Exports as secret port. | P1 - High | Prototype ArtPass placeholder
UI / HUD | Branch minimap panel | BranchMiniMapController | Runtime UI Text/Panel | Panel background, node icons | Minimap panel material | Node/connection icons optional | DoorUnlock/RoomClear optional | Node update pulse optional | Map legend/current/cleared/reward states | Top-right map readability on Windows and VisionOS. | P1 - High | Prototype ArtPass placeholder
UI / HUD | Combat HUD | CombatHudController | Runtime UI Text | Panel/background shapes | HUD panel material/color style | HP/enemy/state icons optional | PlayerHit/RoomClear feedback optional | Text pulse optional | HP, enemies, room state, diagnostics | Needs separation from minimap and economy status. | P1 - High | Prototype ArtPass placeholder
UI / HUD | Economy/status panel | BranchMiniMapController economy panel | Runtime UI Text/Panel | Panel background | Economy panel material | Soul/save icons optional | RewardClaim optional | Counter pulse optional | Run souls, banked souls, rewards, save | Separate from branch map. | P1 - High | Prototype ArtPass placeholder
UI / HUD | Item/reward log panel | BranchMiniMapController item log | Runtime UI Text/Panel | Panel background | Log panel material | Item icons optional | RewardClaim optional | Message slide/fade optional | Latest reward, collected items | Needs clear latest feedback without clutter. | P1 - High | Prototype ArtPass placeholder
VFX | Door unlock VFX | VfxCueId.DoorUnlock / PresentationPrefabRole.VfxDoorUnlock | VFX_VfxDoorUnlock.prefab | Rune flash/pulse | Door unlock material | Rune texture | DoorUnlock | Flash/open pulse | Door state indicator | Important for traversal comprehension. | P1 - High | Prototype ArtPass placeholder
VFX | Enemy death VFX | VfxCueId.EnemyDeath / PresentationPrefabRole.VfxEnemyDeath | VFX_VfxEnemyDeath.prefab | Death burst/poof | Death particle material | Poof/spark texture | EnemyDeath | Pop/dissolve | None | Should communicate removal and splitter spawning. | P1 - High | Prototype ArtPass placeholder
VFX | Enemy hit VFX | VfxCueId.EnemyHit / PresentationPrefabRole.VfxEnemyHit | VFX_VfxEnemyHit.prefab | Hit spark/burst | Hit flash material | Spark texture | EnemyHit | Short burst | None | Must show damage clearly. | P1 - High | Prototype ArtPass placeholder
VFX | Portal complete VFX | VfxCueId.PortalComplete / PresentationPrefabRole.VfxPortalComplete | VFX_VfxPortalComplete.prefab | Portal swirl/transition burst | Portal material | Swirl/noise texture | PortalComplete | Swirl/pulse | Portal label pulse | Needed for hub/next branch transitions. | P1 - High | Prototype ArtPass placeholder
VFX | Projectile fire VFX | VfxCueId.ProjectileFire / PresentationPrefabRole.VfxProjectileFire | VFX_VfxProjectileFire.prefab | Particle prefab/trail | Projectile/fire material | Spark/noise texture | ProjectileFire | Burst/trail | None | Used by player and possibly enemy firing. | P1 - High | Prototype ArtPass placeholder
VFX | Reward claim VFX | VfxCueId.RewardClaim / PresentationPrefabRole.VfxRewardClaim | VFX_VfxRewardClaim.prefab | Sparkle/beam burst | Reward sparkle material | Star/soul texture | RewardClaim | Claim burst | Reward message pulse | Makes rewards feel meaningful. | P1 - High | Prototype ArtPass placeholder
Enemy | Fast Chaser | spawnEnemyFast / EnemyFast / Chaser | AP_EnemyFast.prefab + Enemy_Fast.asset | Lean/agile enemy variant | Amber/speed material | Motion stripe/accent optional | EnemyHit, EnemyDeath | Fast idle jitter, chase, hit | Encounter icon optional | Should read faster than normal even when still. | P2 - Medium | Prototype ArtPass placeholder
Enemy | Heavy Chaser | spawnEnemyHeavy / EnemyHeavy / Chaser | AP_EnemyHeavy.prefab + Enemy_Heavy.asset | Large grounded bulky enemy mesh | Heavy/purple material | Cracked armor/stone texture optional | EnemyHit, EnemyDeath | Heavy idle, slow chase, hit | Encounter icon optional | Should read high HP/contact danger. | P2 - Medium | Prototype ArtPass placeholder
Environment | Hole tile | RoomDesignerCellKinds.Hole / MaterialRole.DesignerHole | Designer/runtime authoring data | Hole void/depth mesh/decal | Dark void edge material | Edge/void texture | Fall/deny VFX later | Subtle shimmer optional | Designer label | Currently mainly designer/export semantics; future gameplay hazard. | P2 - Medium | Prototype ArtPass placeholder
Environment | Treasure / secret room dressing | BranchRoomRole.Treasure / Secret | Currently room role only | Optional chest/cache/decor set | Treasure/secret accent materials | Secret/treasure glyph textures | RewardClaim/Secret reveal | Sparkle/pulse | Secret/reward label optional | Needed to make special rooms feel special. | P2 - Medium | Prototype ArtPass placeholder
Player | Safe start marker | RoomDesignerMarkerKinds.SafeStart / MaterialRole.SpawnSafeStart | Runtime/designer generated marker | Small floor marker or translucent ring | Safe start marker material | Icon/decal optional | Designer place/erase | Gentle pulse optional | Label: spawn_point_safeStart | Visible mostly in designer/debug; not final gameplay art. | P2 - Medium | Prototype ArtPass placeholder
Reward / Item | Ember Charm | Reward_EmberCharm / PassiveItem | Reward pickup generic visual | Flame charm/token mesh | Ember material | Ember icon/emissive mask | RewardClaim | Flame flicker optional | Item icon | Projectile damage effect. | P2 - Medium | Prototype ArtPass placeholder
Reward / Item | Fleet Step | Reward_FleetStep / PassiveItem | Reward pickup generic visual | Boot/feather/step charm mesh | Movement accent material | Icon texture | RewardClaim | Sparkle/step burst optional | Item icon | Move speed effect. | P2 - Medium | Prototype ArtPass placeholder
Reward / Item | Quick Draw | Reward_QuickDraw / Card | Reward pickup generic visual | Card/charm/token mesh | Card material with speed accent | Card face texture/icon | RewardClaim | Card flip optional | Item icon | Shot cooldown effect; should read speed/firing. | P2 - Medium | Prototype ArtPass placeholder
Reward / Item | Stone Heart | Reward_StoneHeart / PassiveItem | Reward pickup generic visual | Heart/stone charm mesh or card art | Stone/heart material | Charm/card texture | RewardClaim | Pickup sparkle | Small item icon | +Max HP and heal; should feel sturdy/protective. | P2 - Medium | Prototype ArtPass placeholder
Room Designer | Inactive door anchor | RoomDesignerDoorKinds.Inactive | Generated port marker | Disabled/ghosted port marker | Inactive port material | Disabled icon optional | DesignerPlace/Erase | None | doorAnchorInactive label | Visible in editor but omitted from runtime doorPorts. | P2 - Medium | Prototype ArtPass placeholder
UI / HUD | Main menu root | MainMenuRoot / MainMenuController | MainMenuRoot.prefab | Menu panels/buttons/card backgrounds | Menu UI materials/colors | Logo/background/profile icons | Button click/transition later | Panel transition optional | New Run, Continue, Challenges, Room Designer, Settings | Player-facing route into all modes. | P2 - Medium | Prototype ArtPass placeholder
UI / HUD | Profile slot card | ProfileSlotCard.prefab | ProfileSlotCard.prefab | Card/panel UI shape | Profile card material/style | Profile icon/progress icons | Select cue later | Hover/select optional | Slot name, runs, banked souls, active run | Needs polish before broader playtests. | P2 - Medium | Prototype ArtPass placeholder
VFX | Room clear VFX | VfxCueId.RoomClear / PresentationPrefabRole.VfxRoomClear | VFX_VfxRoomClear.prefab | Room-level burst/banner | Clear material | Spark/ring texture | RoomClear | Pulse across doors/reward | Room Clear text | Should be celebratory but not noisy. | P2 - Medium | Prototype ArtPass placeholder
Environment | Origin marker / center floor mark | MaterialRole.RoomOriginMarker | Generated marker | Small floor decal/ring mesh | Origin marker material | Decal/icon texture optional | None | None | Label/debug optional | Useful for debugging and room authoring; not necessarily final visible art. | P3 - Low | Prototype ArtPass placeholder
Environment | Spike / hazard tile | Planned tile type | Not yet core runtime visual | Spike/trap mesh | Hazard metal/bone material | Hazard icon/texture | Trigger warning VFX later | Spike pulse/extend optional | Hazard icon | Mentioned in designer concept; should be tracked for physics/logics milestone. | P3 - Planned | Prototype ArtPass placeholder
Reward / Item | Heavy Spark | Reward_HeavySpark / PassiveItem | Reward pickup generic visual | Dense spark/weight charm | Heavy spark material | Icon texture | RewardClaim | Spark pulse optional | Item icon | Damage up but slower cooldown; needs downside readability later. | P3 - Low | Prototype ArtPass placeholder
Reward / Item | Swift Charge | Reward_SwiftCharge / Card | Reward pickup generic visual | Card/token mesh | Swift/charge material | Card icon texture | RewardClaim | Card flip optional | Item icon | Movement and cooldown effect. | P3 - Low | Prototype ArtPass placeholder
VFX | Designer place/erase VFX | VfxCueId.DesignerPlace / DesignerErase | Cue definitions only | Small placement/erase particles | Designer VFX material | Small square/spark texture | DesignerPlace, DesignerErase | Short UI feedback | None | Improves authoring feel. | P3 - Low | Prototype ArtPass placeholder

## Asset Checklist
Required Asset Checklist
Production checklist broken out by entity and asset type. Use Status/Owner/Notes columns as a live tracker.
Group | Entity | Priority | Asset Type | Required Asset | Suggested Owner | Status | Notes
Enemy | Normal Chaser | P0 - Core | 3D mesh/model | Small grounded enemy mesh | Rafal | Needed / placeholder
Enemy | Normal Chaser | P0 - Core | Material | Red/corrupt enemy material | Rafal | Needed / placeholder
Enemy | Normal Chaser | P0 - Core | Texture set | Base color, roughness, optional eye/glow | Rafal | Needed / placeholder
Enemy | Normal Chaser | P0 - Core | VFX | EnemyHit, EnemyDeath | Rafal + Martin | Needed / placeholder
Enemy | Normal Chaser | P0 - Core | Animation | Idle, chase wobble, hit, death pop | Rafal | Needed / placeholder
Enemy | Normal Chaser | P0 - Core | UI/Icon/Label | Encounter icon optional | Rafal + Martin | Needed / placeholder
Enemy | Stone Warden boss | P0 - Core | 3D mesh/model | Large boss silhouette, stone guardian body | Rafal | Needed / placeholder
Enemy | Stone Warden boss | P0 - Core | Material | Stone, moss/ember cracks, boss accent | Rafal | Needed / placeholder
Enemy | Stone Warden boss | P0 - Core | Texture set | Stone normal, crack/emissive mask optional | Rafal | Needed / placeholder
Enemy | Stone Warden boss | P0 - Core | VFX | Charge, projectile burst, EnemyHit, EnemyDeath | Rafal + Martin | Needed / placeholder
Enemy | Stone Warden boss | P0 - Core | Animation | Idle, slow pursue, charge windup, low-health burst, death | Rafal | Needed / placeholder
Enemy | Stone Warden boss | P0 - Core | UI/Icon/Label | Boss icon/nameplate later | Rafal + Martin | Needed / placeholder
Environment | Door active/open | P0 - Core | 3D mesh/model | Door/gate active marker mesh | Rafal | Needed / placeholder
Environment | Door active/open | P0 - Core | Material | Active door material | Rafal | Needed / placeholder
Environment | Door active/open | P0 - Core | Texture set | Door rune texture | Rafal | Needed / placeholder
Environment | Door active/open | P0 - Core | VFX | DoorUnlock | Rafal + Martin | Needed / placeholder
Environment | Door active/open | P0 - Core | Animation | Open/activate pulse | Rafal | Needed / placeholder
Environment | Door active/open | P0 - Core | UI/Icon/Label | Arrow/door icon optional | Rafal + Martin | Needed / placeholder
Environment | Door locked | P0 - Core | 3D mesh/model | Door frame/slab/gate mesh | Rafal | Needed / placeholder
Environment | Door locked | P0 - Core | Material | Locked door material | Rafal | Needed / placeholder
Environment | Door locked | P0 - Core | Texture set | Lock/rune texture | Rafal | Needed / placeholder
Environment | Door locked | P0 - Core | VFX | DoorUnlock | Rafal + Martin | Needed / placeholder
Environment | Door locked | P0 - Core | Animation | Lock pulse/shake optional | Rafal | Needed / placeholder
Environment | Door locked | P0 - Core | UI/Icon/Label | Lock icon optional | Rafal + Martin | Needed / placeholder
Environment | Hub return / boss portal | P0 - Core | 3D mesh/model | Portal ring/pool/gate mesh | Rafal | Needed / placeholder
Environment | Hub return / boss portal | P0 - Core | Material | Portal material | Rafal | Needed / placeholder
Environment | Hub return / boss portal | P0 - Core | Texture set | Swirl/noise/emissive texture | Rafal | Needed / placeholder
Environment | Hub return / boss portal | P0 - Core | VFX | PortalComplete | Rafal + Martin | Needed / placeholder
Environment | Hub return / boss portal | P0 - Core | Animation | Swirl/pulse | Rafal | Needed / placeholder
Environment | Hub return / boss portal | P0 - Core | UI/Icon/Label | Portal label optional | Rafal + Martin | Needed / placeholder
Environment | Inter-branch hub shop stand | P0 - Core | 3D mesh/model | Shop stand/table/pedestal mesh | Rafal | Needed / placeholder
Environment | Inter-branch hub shop stand | P0 - Core | Material | Shop wood/stone/cloth material | Rafal | Needed / placeholder
Environment | Inter-branch hub shop stand | P0 - Core | Texture set | Shop sign/card texture | Rafal | Needed / placeholder
Environment | Inter-branch hub shop stand | P0 - Core | VFX | Purchase/RewardClaim later | Rafal + Martin | Needed / placeholder
Environment | Inter-branch hub shop stand | P0 - Core | Animation | Idle candle/pulse optional | Rafal | Needed / placeholder
Environment | Inter-branch hub shop stand | P0 - Core | UI/Icon/Label | Shop label/card text | Rafal + Martin | Needed / placeholder
Environment | Next branch portal | P0 - Core | 3D mesh/model | Portal/card/gate mesh for branch choices | Rafal | Needed / placeholder
Environment | Next branch portal | P0 - Core | Material | Next portal material | Rafal | Needed / placeholder
Environment | Next branch portal | P0 - Core | Texture set | Seed/branch rune texture | Rafal | Needed / placeholder
Environment | Next branch portal | P0 - Core | VFX | PortalComplete | Rafal + Martin | Needed / placeholder
Environment | Next branch portal | P0 - Core | Animation | Idle swirl/pulse | Rafal | Needed / placeholder
Environment | Next branch portal | P0 - Core | UI/Icon/Label | Portal card text/seed | Rafal + Martin | Needed / placeholder
Environment | Rock obstacle block | P0 - Core | 3D mesh/model | 1m obstacle mesh, top at 1m, bottom at floor | Rafal | Needed / placeholder
Environment | Rock obstacle block | P0 - Core | Material | Rock/stone/block material | Rafal | Needed / placeholder
Environment | Rock obstacle block | P0 - Core | Texture set | Stone albedo/normal/roughness | Rafal | Needed / placeholder
Environment | Rock obstacle block | P0 - Core | VFX | Projectile hit optional | Rafal + Martin | Needed / placeholder
Environment | Rock obstacle block | P0 - Core | Animation | None or tiny hit shake | Rafal | Needed / placeholder
Environment | Room floor | P0 - Core | 3D mesh/model | Tile/floor slab mesh or modular plane | Rafal | Needed / placeholder
Environment | Room floor | P0 - Core | Material | Dark toy-diorama floor material | Rafal | Needed / placeholder
Environment | Room floor | P0 - Core | Texture set | Albedo, roughness, normal, grid/wear masks | Rafal | Needed / placeholder
Environment | Room floor | P0 - Core | VFX | RoomClear optional | Rafal + Martin | Needed / placeholder
Environment | Shop cards | P0 - Core | 3D mesh/model | Three card meshes or world-space UI cards | Rafal | Needed / placeholder
Environment | Shop cards | P0 - Core | Material | Card normal/affordable/sold materials | Rafal | Needed / placeholder
Environment | Shop cards | P0 - Core | Texture set | Card face/icon textures | Rafal | Needed / placeholder
Environment | Shop cards | P0 - Core | VFX | Purchase success/fail cue later | Rafal + Martin | Needed / placeholder
Environment | Shop cards | P0 - Core | Animation | Hover/affordable pulse, sold dim | Rafal | Needed / placeholder
Environment | Shop cards | P0 - Core | UI/Icon/Label | Offer name, price, effect, SOLD/Need souls | Rafal + Martin | Needed / placeholder
Player | Player character | P0 - Core | 3D mesh/model | 1 readable player body mesh; optional head/body split; meter-scale pivot at feet/center | Rafal | Needed / placeholder
Player | Player character | P0 - Core | Material | Player body material, accent/emissive soul material | Rafal | Needed / placeholder
Player | Player character | P0 - Core | Texture set | Base color, roughness/normal optional, small accent mask | Rafal | Needed / placeholder
Player | Player character | P0 - Core | VFX | Player hit cue; optional spawn/respawn cue | Rafal + Martin | Needed / placeholder
Player | Player character | P0 - Core | Animation | Idle breathing/bob, hit flinch, optional run lean | Rafal | Needed / placeholder
Player | Player character | P0 - Core | UI/Icon/Label | HUD portrait/icon later | Rafal + Martin | Needed / placeholder
Player | Player projectile | P0 - Core | 3D mesh/model | Small orb/bolt mesh or billboard | Rafal | Needed / placeholder
Player | Player projectile | P0 - Core | Material | Bright projectile material | Rafal | Needed / placeholder
Player | Player projectile | P0 - Core | Texture set | Glow/noise texture optional | Rafal | Needed / placeholder
Player | Player projectile | P0 - Core | VFX | ProjectileFire, enemy hit impact | Rafal + Martin | Needed / placeholder
Player | Player projectile | P0 - Core | Animation | Looping spin/trail optional | Rafal | Needed / placeholder
Reward / Item | Boss key pickup | P0 - Core | 3D mesh/model | Key/fragment/glyph mesh | Rafal | Needed / placeholder
Reward / Item | Boss key pickup | P0 - Core | Material | Boss key gold/ember material | Rafal | Needed / placeholder
Reward / Item | Boss key pickup | P0 - Core | Texture set | Key/rune texture optional | Rafal | Needed / placeholder
Reward / Item | Boss key pickup | P0 - Core | VFX | RewardClaim or DoorUnlock | Rafal + Martin | Needed / placeholder
Reward / Item | Boss key pickup | P0 - Core | Animation | Bob, sparkle, claim pop | Rafal | Needed / placeholder
Reward / Item | Boss key pickup | P0 - Core | UI/Icon/Label | Boss key HUD icon later | Rafal + Martin | Needed / placeholder
Reward / Item | Generic room reward pickup | P0 - Core | 3D mesh/model | Pickup pedestal/orb/chest-like mesh | Rafal | Needed / placeholder
Reward / Item | Generic room reward pickup | P0 - Core | Material | Reward glow material | Rafal | Needed / placeholder
Reward / Item | Generic room reward pickup | P0 - Core | Texture set | Sparkle/emissive texture optional | Rafal | Needed / placeholder
Reward / Item | Generic room reward pickup | P0 - Core | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Generic room reward pickup | P0 - Core | Animation | Idle bob, claim pop | Rafal | Needed / placeholder
Reward / Item | Generic room reward pickup | P0 - Core | UI/Icon/Label | Reward message in HUD | Rafal + Martin | Needed / placeholder
Room Designer | Designer cursor | P0 - Core | 3D mesh/model | Cursor highlight box/ring | Rafal | Needed / placeholder
Room Designer | Designer cursor | P0 - Core | Material | Cursor highlight material | Rafal | Needed / placeholder
Room Designer | Designer cursor | P0 - Core | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Designer cursor | P0 - Core | Animation | Cursor pulse optional | Rafal | Needed / placeholder
Room Designer | Designer cursor | P0 - Core | UI/Icon/Label | Cursor coordinate label | Rafal + Martin | Needed / placeholder
UI / HUD | Shop offer text/card UI | P0 - Core | 3D mesh/model | World-space card/panel mesh | Rafal | Needed / placeholder
UI / HUD | Shop offer text/card UI | P0 - Core | Material | Affordable/unaffordable/sold materials | Rafal | Needed / placeholder
UI / HUD | Shop offer text/card UI | P0 - Core | Texture set | Offer icons/card art | Rafal | Needed / placeholder
UI / HUD | Shop offer text/card UI | P0 - Core | VFX | Purchase/fail cue later | Rafal + Martin | Needed / placeholder
UI / HUD | Shop offer text/card UI | P0 - Core | Animation | Affordable pulse, sold dim | Rafal | Needed / placeholder
UI / HUD | Shop offer text/card UI | P0 - Core | UI/Icon/Label | Name, price, effect, SOLD/Need souls | Rafal + Martin | Needed / placeholder
Enemy | Ash Charger | P1 - High | 3D mesh/model | Pointed/forward-leaning charger mesh | Rafal | Needed / placeholder
Enemy | Ash Charger | P1 - High | Material | Orange ember/charge material | Rafal | Needed / placeholder
Enemy | Ash Charger | P1 - High | Texture set | Heat/crack texture optional | Rafal | Needed / placeholder
Enemy | Ash Charger | P1 - High | VFX | Charge windup, EnemyHit, EnemyDeath | Rafal + Martin | Needed / placeholder
Enemy | Ash Charger | P1 - High | Animation | Windup, charge burst, recovery | Rafal | Needed / placeholder
Enemy | Ash Charger | P1 - High | UI/Icon/Label | Encounter icon optional | Rafal + Martin | Needed / placeholder
Enemy | Bone Turret | P1 - High | 3D mesh/model | Stationary turret/statue/eye mesh | Rafal | Needed / placeholder
Enemy | Bone Turret | P1 - High | Material | Bone/stone + projectile accent | Rafal | Needed / placeholder
Enemy | Bone Turret | P1 - High | Texture set | Bone/stone texture optional | Rafal | Needed / placeholder
Enemy | Bone Turret | P1 - High | VFX | Enemy projectile fire, EnemyHit, EnemyDeath | Rafal + Martin | Needed / placeholder
Enemy | Bone Turret | P1 - High | Animation | Aim turn, fire recoil, hit | Rafal | Needed / placeholder
Enemy | Bone Turret | P1 - High | UI/Icon/Label | Encounter icon optional | Rafal + Martin | Needed / placeholder
Enemy | Enemy projectile | P1 - High | 3D mesh/model | Small hostile bolt/orb mesh | Rafal | Needed / placeholder
Enemy | Enemy projectile | P1 - High | Material | Hostile projectile material distinct from player | Rafal | Needed / placeholder
Enemy | Enemy projectile | P1 - High | Texture set | Glow/noise texture optional | Rafal | Needed / placeholder
Enemy | Enemy projectile | P1 - High | VFX | Projectile fire and player hit | Rafal + Martin | Needed / placeholder
Enemy | Enemy projectile | P1 - High | Animation | Spin/trail optional | Rafal | Needed / placeholder
Enemy | Flying Chaser | P1 - High | 3D mesh/model | Floating enemy mesh with wings/orb/soul form | Rafal | Needed / placeholder
Enemy | Flying Chaser | P1 - High | Material | Blue/airborne enemy material | Rafal | Needed / placeholder
Enemy | Flying Chaser | P1 - High | Texture set | Wing/soul texture optional | Rafal | Needed / placeholder
Enemy | Flying Chaser | P1 - High | VFX | EnemyHit, EnemyDeath | Rafal + Martin | Needed / placeholder
Enemy | Flying Chaser | P1 - High | Animation | Hover loop, hit, death | Rafal | Needed / placeholder
Enemy | Flying Chaser | P1 - High | UI/Icon/Label | Encounter icon optional | Rafal + Martin | Needed / placeholder
Enemy | Husk Splitter | P1 - High | 3D mesh/model | Fragile pod/husk mesh | Rafal | Needed / placeholder
Enemy | Husk Splitter | P1 - High | Material | Green split/swarm material | Rafal | Needed / placeholder
Enemy | Husk Splitter | P1 - High | Texture set | Crack/shell texture optional | Rafal | Needed / placeholder
Enemy | Husk Splitter | P1 - High | VFX | Split/death burst, EnemyHit | Rafal + Martin | Needed / placeholder
Enemy | Husk Splitter | P1 - High | Animation | Pulse before split, pop death | Rafal | Needed / placeholder
Enemy | Husk Splitter | P1 - High | UI/Icon/Label | Encounter icon optional | Rafal + Martin | Needed / placeholder
Environment | Door cleared | P1 - High | 3D mesh/model | Cleared/open door variant | Rafal | Needed / placeholder
Environment | Door cleared | P1 - High | Material | Cleared/greenish material | Rafal | Needed / placeholder
Environment | Door cleared | P1 - High | Texture set | Glow/rune texture | Rafal | Needed / placeholder
Environment | Door cleared | P1 - High | VFX | RoomClear/DoorUnlock | Rafal + Martin | Needed / placeholder
Environment | Door cleared | P1 - High | Animation | Clear flash optional | Rafal | Needed / placeholder
Environment | Door unavailable | P1 - High | 3D mesh/model | Disabled/decorative door marker | Rafal | Needed / placeholder
Environment | Door unavailable | P1 - High | Material | Muted unavailable material | Rafal | Needed / placeholder
Environment | Door unavailable | P1 - High | Texture set | Cracked/blocked texture | Rafal | Needed / placeholder
Environment | Secret door debug marker | P1 - High | 3D mesh/model | Secret wall/door marker mesh | Rafal | Needed / placeholder
Environment | Secret door debug marker | P1 - High | Material | Secret door material | Rafal | Needed / placeholder
Environment | Secret door debug marker | P1 - High | Texture set | Secret glyph texture | Rafal | Needed / placeholder
Environment | Secret door debug marker | P1 - High | VFX | DoorUnlock optional | Rafal + Martin | Needed / placeholder
Environment | Secret door debug marker | P1 - High | Animation | Pulse/hidden reveal optional | Rafal | Needed / placeholder
Environment | Secret door debug marker | P1 - High | UI/Icon/Label | Secret icon optional | Rafal + Martin | Needed / placeholder
Player | Player hit feedback | P1 - High | 3D mesh/model | Particle/burst visual | Rafal | Needed / placeholder
Player | Player hit feedback | P1 - High | Material | Damage flash material | Rafal | Needed / placeholder
Player | Player hit feedback | P1 - High | Texture set | Hit spark/noise texture optional | Rafal | Needed / placeholder
Player | Player hit feedback | P1 - High | VFX | PlayerHit | Rafal + Martin | Needed / placeholder
Player | Player hit feedback | P1 - High | Animation | Brief flash/pulse | Rafal | Needed / placeholder
Player | Player hit feedback | P1 - High | UI/Icon/Label | HP feedback in HUD | Rafal + Martin | Needed / placeholder
Reward / Item | Boss Sigil | P1 - High | 3D mesh/model | Large sigil/crest mesh | Rafal | Needed / placeholder
Reward / Item | Boss Sigil | P1 - High | Material | Boss reward material | Rafal | Needed / placeholder
Reward / Item | Boss Sigil | P1 - High | Texture set | Sigil texture/emissive mask | Rafal | Needed / placeholder
Reward / Item | Boss Sigil | P1 - High | VFX | RewardClaim, RoomClear | Rafal + Martin | Needed / placeholder
Reward / Item | Boss Sigil | P1 - High | Animation | Hover, pulse, claim burst | Rafal | Needed / placeholder
Reward / Item | Boss Sigil | P1 - High | UI/Icon/Label | Boss reward icon | Rafal + Martin | Needed / placeholder
Reward / Item | Heal shop offer | P1 - High | 3D mesh/model | Card/potion/heal token mesh or UI card face | Rafal | Needed / placeholder
Reward / Item | Heal shop offer | P1 - High | Material | Healing card material | Rafal | Needed / placeholder
Reward / Item | Heal shop offer | P1 - High | Texture set | Heart/potion icon texture | Rafal | Needed / placeholder
Reward / Item | Heal shop offer | P1 - High | VFX | RewardClaim/Shop purchase later | Rafal + Martin | Needed / placeholder
Reward / Item | Heal shop offer | P1 - High | Animation | Card pulse on affordable | Rafal | Needed / placeholder
Reward / Item | Heal shop offer | P1 - High | UI/Icon/Label | Shop card text/icon | Rafal + Martin | Needed / placeholder
Reward / Item | Soul currency pickup/cache | P1 - High | 3D mesh/model | Soul orb/cache variant or coin cluster | Rafal | Needed / placeholder
Reward / Item | Soul currency pickup/cache | P1 - High | Material | Soul currency material | Rafal | Needed / placeholder
Reward / Item | Soul currency pickup/cache | P1 - High | Texture set | Soul swirl/noise optional | Rafal | Needed / placeholder
Reward / Item | Soul currency pickup/cache | P1 - High | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Soul currency pickup/cache | P1 - High | Animation | Bob, sparkle | Rafal | Needed / placeholder
Reward / Item | Soul currency pickup/cache | P1 - High | UI/Icon/Label | Soul icon for HUD/shop | Rafal + Martin | Needed / placeholder
Room Designer | Active door anchor | P1 - High | 3D mesh/model | Active door marker | Rafal | Needed / placeholder
Room Designer | Active door anchor | P1 - High | Material | Active door material | Rafal | Needed / placeholder
Room Designer | Active door anchor | P1 - High | Texture set | Door icon/glyph | Rafal | Needed / placeholder
Room Designer | Active door anchor | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Active door anchor | P1 - High | Animation | Pulse optional | Rafal | Needed / placeholder
Room Designer | Active door anchor | P1 - High | UI/Icon/Label | doorAnchorActive label | Rafal + Martin | Needed / placeholder
Room Designer | Available door anchor | P1 - High | 3D mesh/model | Door anchor ghost marker | Rafal | Needed / placeholder
Room Designer | Available door anchor | P1 - High | Material | Available anchor material | Rafal | Needed / placeholder
Room Designer | Available door anchor | P1 - High | Texture set | Port icon/glyph optional | Rafal | Needed / placeholder
Room Designer | Available door anchor | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Available door anchor | P1 - High | Animation | Pulse optional | Rafal | Needed / placeholder
Room Designer | Available door anchor | P1 - High | UI/Icon/Label | doorAnchorAvailable label | Rafal + Martin | Needed / placeholder
Room Designer | Designer grid | P1 - High | 3D mesh/model | Thin grid line mesh/cubes | Rafal | Needed / placeholder
Room Designer | Designer grid | P1 - High | Material | Designer grid material | Rafal | Needed / placeholder
Room Designer | Designer grid | P1 - High | VFX | Designer place/erase | Rafal + Martin | Needed / placeholder
Room Designer | Designer grid | P1 - High | UI/Icon/Label | Grid labels optional | Rafal + Martin | Needed / placeholder
Room Designer | Designer ground tile | P1 - High | 3D mesh/model | 1m ground block/slab | Rafal | Needed / placeholder
Room Designer | Designer ground tile | P1 - High | Material | Designer ground material | Rafal | Needed / placeholder
Room Designer | Designer ground tile | P1 - High | Texture set | Tile texture optional | Rafal | Needed / placeholder
Room Designer | Designer ground tile | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Designer ground tile | P1 - High | UI/Icon/Label | tileGround label | Rafal + Martin | Needed / placeholder
Room Designer | Designer hole tile | P1 - High | 3D mesh/model | Hole/void preview tile | Rafal | Needed / placeholder
Room Designer | Designer hole tile | P1 - High | Material | Designer hole material | Rafal | Needed / placeholder
Room Designer | Designer hole tile | P1 - High | Texture set | Void texture optional | Rafal | Needed / placeholder
Room Designer | Designer hole tile | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Designer hole tile | P1 - High | UI/Icon/Label | tileHole label | Rafal + Martin | Needed / placeholder
Room Designer | Designer labels / panels | P1 - High | 3D mesh/model | World-space label panels optional | Rafal | Needed / placeholder
Room Designer | Designer labels / panels | P1 - High | Material | Panel/text materials | Rafal | Needed / placeholder
Room Designer | Designer labels / panels | P1 - High | Texture set | Icons for tools/ports later | Rafal | Needed / placeholder
Room Designer | Designer labels / panels | P1 - High | VFX | DesignerPlace/Erase cues | Rafal + Martin | Needed / placeholder
Room Designer | Designer labels / panels | P1 - High | Animation | Panel transitions optional | Rafal | Needed / placeholder
Room Designer | Designer labels / panels | P1 - High | UI/Icon/Label | Tool, footprint, validation, controls | Rafal + Martin | Needed / placeholder
Room Designer | Designer rock tile | P1 - High | 3D mesh/model | 1m rock/block preview | Rafal | Needed / placeholder
Room Designer | Designer rock tile | P1 - High | Material | Designer rock material | Rafal | Needed / placeholder
Room Designer | Designer rock tile | P1 - High | Texture set | Rock texture optional | Rafal | Needed / placeholder
Room Designer | Designer rock tile | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Designer rock tile | P1 - High | UI/Icon/Label | tileRock label | Rafal + Martin | Needed / placeholder
Room Designer | Enemy spawn marker | P1 - High | 3D mesh/model | Small colored marker/silhouette | Rafal | Needed / placeholder
Room Designer | Enemy spawn marker | P1 - High | Material | Enemy spawn marker materials per variant | Rafal | Needed / placeholder
Room Designer | Enemy spawn marker | P1 - High | Texture set | Variant icons | Rafal | Needed / placeholder
Room Designer | Enemy spawn marker | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Enemy spawn marker | P1 - High | Animation | Pulse optional | Rafal | Needed / placeholder
Room Designer | Enemy spawn marker | P1 - High | UI/Icon/Label | spawn_point_enemy_* labels | Rafal + Martin | Needed / placeholder
Room Designer | Reward spawn marker | P1 - High | 3D mesh/model | Reward anchor marker | Rafal | Needed / placeholder
Room Designer | Reward spawn marker | P1 - High | Material | Reward marker material | Rafal | Needed / placeholder
Room Designer | Reward spawn marker | P1 - High | Texture set | Reward icon | Rafal | Needed / placeholder
Room Designer | Reward spawn marker | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Reward spawn marker | P1 - High | Animation | Pulse optional | Rafal | Needed / placeholder
Room Designer | Reward spawn marker | P1 - High | UI/Icon/Label | spawn_point_roomReward label | Rafal + Martin | Needed / placeholder
Room Designer | Safe start marker | P1 - High | 3D mesh/model | Safe start marker | Rafal | Needed / placeholder
Room Designer | Safe start marker | P1 - High | Material | Safe marker material | Rafal | Needed / placeholder
Room Designer | Safe start marker | P1 - High | Texture set | Start icon | Rafal | Needed / placeholder
Room Designer | Safe start marker | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Safe start marker | P1 - High | Animation | Pulse optional | Rafal | Needed / placeholder
Room Designer | Safe start marker | P1 - High | UI/Icon/Label | spawn_point_safeStart label | Rafal + Martin | Needed / placeholder
Room Designer | Secret door anchor | P1 - High | 3D mesh/model | Secret door marker | Rafal | Needed / placeholder
Room Designer | Secret door anchor | P1 - High | Material | Secret door material | Rafal | Needed / placeholder
Room Designer | Secret door anchor | P1 - High | Texture set | Secret glyph | Rafal | Needed / placeholder
Room Designer | Secret door anchor | P1 - High | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Secret door anchor | P1 - High | Animation | Pulse optional | Rafal | Needed / placeholder
Room Designer | Secret door anchor | P1 - High | UI/Icon/Label | doorAnchorSecret label | Rafal + Martin | Needed / placeholder
UI / HUD | Branch minimap panel | P1 - High | 3D mesh/model | Panel background, node icons | Rafal | Needed / placeholder
UI / HUD | Branch minimap panel | P1 - High | Material | Minimap panel material | Rafal | Needed / placeholder
UI / HUD | Branch minimap panel | P1 - High | Texture set | Node/connection icons optional | Rafal | Needed / placeholder
UI / HUD | Branch minimap panel | P1 - High | VFX | DoorUnlock/RoomClear optional | Rafal + Martin | Needed / placeholder
UI / HUD | Branch minimap panel | P1 - High | Animation | Node update pulse optional | Rafal | Needed / placeholder
UI / HUD | Branch minimap panel | P1 - High | UI/Icon/Label | Map legend/current/cleared/reward states | Rafal + Martin | Needed / placeholder
UI / HUD | Combat HUD | P1 - High | 3D mesh/model | Panel/background shapes | Rafal | Needed / placeholder
UI / HUD | Combat HUD | P1 - High | Material | HUD panel material/color style | Rafal | Needed / placeholder
UI / HUD | Combat HUD | P1 - High | Texture set | HP/enemy/state icons optional | Rafal | Needed / placeholder
UI / HUD | Combat HUD | P1 - High | VFX | PlayerHit/RoomClear feedback optional | Rafal + Martin | Needed / placeholder
UI / HUD | Combat HUD | P1 - High | Animation | Text pulse optional | Rafal | Needed / placeholder
UI / HUD | Combat HUD | P1 - High | UI/Icon/Label | HP, enemies, room state, diagnostics | Rafal + Martin | Needed / placeholder
UI / HUD | Economy/status panel | P1 - High | 3D mesh/model | Panel background | Rafal | Needed / placeholder
UI / HUD | Economy/status panel | P1 - High | Material | Economy panel material | Rafal | Needed / placeholder
UI / HUD | Economy/status panel | P1 - High | Texture set | Soul/save icons optional | Rafal | Needed / placeholder
UI / HUD | Economy/status panel | P1 - High | VFX | RewardClaim optional | Rafal + Martin | Needed / placeholder
UI / HUD | Economy/status panel | P1 - High | Animation | Counter pulse optional | Rafal | Needed / placeholder
UI / HUD | Economy/status panel | P1 - High | UI/Icon/Label | Run souls, banked souls, rewards, save | Rafal + Martin | Needed / placeholder
UI / HUD | Item/reward log panel | P1 - High | 3D mesh/model | Panel background | Rafal | Needed / placeholder
UI / HUD | Item/reward log panel | P1 - High | Material | Log panel material | Rafal | Needed / placeholder
UI / HUD | Item/reward log panel | P1 - High | Texture set | Item icons optional | Rafal | Needed / placeholder
UI / HUD | Item/reward log panel | P1 - High | VFX | RewardClaim optional | Rafal + Martin | Needed / placeholder
UI / HUD | Item/reward log panel | P1 - High | Animation | Message slide/fade optional | Rafal | Needed / placeholder
UI / HUD | Item/reward log panel | P1 - High | UI/Icon/Label | Latest reward, collected items | Rafal + Martin | Needed / placeholder
VFX | Door unlock VFX | P1 - High | 3D mesh/model | Rune flash/pulse | Rafal | Needed / placeholder
VFX | Door unlock VFX | P1 - High | Material | Door unlock material | Rafal | Needed / placeholder
VFX | Door unlock VFX | P1 - High | Texture set | Rune texture | Rafal | Needed / placeholder
VFX | Door unlock VFX | P1 - High | VFX | DoorUnlock | Rafal + Martin | Needed / placeholder
VFX | Door unlock VFX | P1 - High | Animation | Flash/open pulse | Rafal | Needed / placeholder
VFX | Door unlock VFX | P1 - High | UI/Icon/Label | Door state indicator | Rafal + Martin | Needed / placeholder
VFX | Enemy death VFX | P1 - High | 3D mesh/model | Death burst/poof | Rafal | Needed / placeholder
VFX | Enemy death VFX | P1 - High | Material | Death particle material | Rafal | Needed / placeholder
VFX | Enemy death VFX | P1 - High | Texture set | Poof/spark texture | Rafal | Needed / placeholder
VFX | Enemy death VFX | P1 - High | VFX | EnemyDeath | Rafal + Martin | Needed / placeholder
VFX | Enemy death VFX | P1 - High | Animation | Pop/dissolve | Rafal | Needed / placeholder
VFX | Enemy hit VFX | P1 - High | 3D mesh/model | Hit spark/burst | Rafal | Needed / placeholder
VFX | Enemy hit VFX | P1 - High | Material | Hit flash material | Rafal | Needed / placeholder
VFX | Enemy hit VFX | P1 - High | Texture set | Spark texture | Rafal | Needed / placeholder
VFX | Enemy hit VFX | P1 - High | VFX | EnemyHit | Rafal + Martin | Needed / placeholder
VFX | Enemy hit VFX | P1 - High | Animation | Short burst | Rafal | Needed / placeholder
VFX | Portal complete VFX | P1 - High | 3D mesh/model | Portal swirl/transition burst | Rafal | Needed / placeholder
VFX | Portal complete VFX | P1 - High | Material | Portal material | Rafal | Needed / placeholder
VFX | Portal complete VFX | P1 - High | Texture set | Swirl/noise texture | Rafal | Needed / placeholder
VFX | Portal complete VFX | P1 - High | VFX | PortalComplete | Rafal + Martin | Needed / placeholder
VFX | Portal complete VFX | P1 - High | Animation | Swirl/pulse | Rafal | Needed / placeholder
VFX | Portal complete VFX | P1 - High | UI/Icon/Label | Portal label pulse | Rafal + Martin | Needed / placeholder
VFX | Projectile fire VFX | P1 - High | 3D mesh/model | Particle prefab/trail | Rafal | Needed / placeholder
VFX | Projectile fire VFX | P1 - High | Material | Projectile/fire material | Rafal | Needed / placeholder
VFX | Projectile fire VFX | P1 - High | Texture set | Spark/noise texture | Rafal | Needed / placeholder
VFX | Projectile fire VFX | P1 - High | VFX | ProjectileFire | Rafal + Martin | Needed / placeholder
VFX | Projectile fire VFX | P1 - High | Animation | Burst/trail | Rafal | Needed / placeholder
VFX | Reward claim VFX | P1 - High | 3D mesh/model | Sparkle/beam burst | Rafal | Needed / placeholder
VFX | Reward claim VFX | P1 - High | Material | Reward sparkle material | Rafal | Needed / placeholder
VFX | Reward claim VFX | P1 - High | Texture set | Star/soul texture | Rafal | Needed / placeholder
VFX | Reward claim VFX | P1 - High | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
VFX | Reward claim VFX | P1 - High | Animation | Claim burst | Rafal | Needed / placeholder
VFX | Reward claim VFX | P1 - High | UI/Icon/Label | Reward message pulse | Rafal + Martin | Needed / placeholder
Enemy | Fast Chaser | P2 - Medium | 3D mesh/model | Lean/agile enemy variant | Rafal | Needed / placeholder
Enemy | Fast Chaser | P2 - Medium | Material | Amber/speed material | Rafal | Needed / placeholder
Enemy | Fast Chaser | P2 - Medium | Texture set | Motion stripe/accent optional | Rafal | Needed / placeholder
Enemy | Fast Chaser | P2 - Medium | VFX | EnemyHit, EnemyDeath | Rafal + Martin | Needed / placeholder
Enemy | Fast Chaser | P2 - Medium | Animation | Fast idle jitter, chase, hit | Rafal | Needed / placeholder
Enemy | Fast Chaser | P2 - Medium | UI/Icon/Label | Encounter icon optional | Rafal + Martin | Needed / placeholder
Enemy | Heavy Chaser | P2 - Medium | 3D mesh/model | Large grounded bulky enemy mesh | Rafal | Needed / placeholder
Enemy | Heavy Chaser | P2 - Medium | Material | Heavy/purple material | Rafal | Needed / placeholder
Enemy | Heavy Chaser | P2 - Medium | Texture set | Cracked armor/stone texture optional | Rafal | Needed / placeholder
Enemy | Heavy Chaser | P2 - Medium | VFX | EnemyHit, EnemyDeath | Rafal + Martin | Needed / placeholder
Enemy | Heavy Chaser | P2 - Medium | Animation | Heavy idle, slow chase, hit | Rafal | Needed / placeholder
Enemy | Heavy Chaser | P2 - Medium | UI/Icon/Label | Encounter icon optional | Rafal + Martin | Needed / placeholder
Environment | Hole tile | P2 - Medium | 3D mesh/model | Hole void/depth mesh/decal | Rafal | Needed / placeholder
Environment | Hole tile | P2 - Medium | Material | Dark void edge material | Rafal | Needed / placeholder
Environment | Hole tile | P2 - Medium | Texture set | Edge/void texture | Rafal | Needed / placeholder
Environment | Hole tile | P2 - Medium | VFX | Fall/deny VFX later | Rafal + Martin | Needed / placeholder
Environment | Hole tile | P2 - Medium | Animation | Subtle shimmer optional | Rafal | Needed / placeholder
Environment | Hole tile | P2 - Medium | UI/Icon/Label | Designer label | Rafal + Martin | Needed / placeholder
Environment | Treasure / secret room dressing | P2 - Medium | 3D mesh/model | Optional chest/cache/decor set | Rafal | Needed / placeholder
Environment | Treasure / secret room dressing | P2 - Medium | Material | Treasure/secret accent materials | Rafal | Needed / placeholder
Environment | Treasure / secret room dressing | P2 - Medium | Texture set | Secret/treasure glyph textures | Rafal | Needed / placeholder
Environment | Treasure / secret room dressing | P2 - Medium | VFX | RewardClaim/Secret reveal | Rafal + Martin | Needed / placeholder
Environment | Treasure / secret room dressing | P2 - Medium | Animation | Sparkle/pulse | Rafal | Needed / placeholder
Environment | Treasure / secret room dressing | P2 - Medium | UI/Icon/Label | Secret/reward label optional | Rafal + Martin | Needed / placeholder
Player | Safe start marker | P2 - Medium | 3D mesh/model | Small floor marker or translucent ring | Rafal | Needed / placeholder
Player | Safe start marker | P2 - Medium | Material | Safe start marker material | Rafal | Needed / placeholder
Player | Safe start marker | P2 - Medium | Texture set | Icon/decal optional | Rafal | Needed / placeholder
Player | Safe start marker | P2 - Medium | VFX | Designer place/erase | Rafal + Martin | Needed / placeholder
Player | Safe start marker | P2 - Medium | Animation | Gentle pulse optional | Rafal | Needed / placeholder
Player | Safe start marker | P2 - Medium | UI/Icon/Label | Label: spawn_point_safeStart | Rafal + Martin | Needed / placeholder
Reward / Item | Ember Charm | P2 - Medium | 3D mesh/model | Flame charm/token mesh | Rafal | Needed / placeholder
Reward / Item | Ember Charm | P2 - Medium | Material | Ember material | Rafal | Needed / placeholder
Reward / Item | Ember Charm | P2 - Medium | Texture set | Ember icon/emissive mask | Rafal | Needed / placeholder
Reward / Item | Ember Charm | P2 - Medium | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Ember Charm | P2 - Medium | Animation | Flame flicker optional | Rafal | Needed / placeholder
Reward / Item | Ember Charm | P2 - Medium | UI/Icon/Label | Item icon | Rafal + Martin | Needed / placeholder
Reward / Item | Fleet Step | P2 - Medium | 3D mesh/model | Boot/feather/step charm mesh | Rafal | Needed / placeholder
Reward / Item | Fleet Step | P2 - Medium | Material | Movement accent material | Rafal | Needed / placeholder
Reward / Item | Fleet Step | P2 - Medium | Texture set | Icon texture | Rafal | Needed / placeholder
Reward / Item | Fleet Step | P2 - Medium | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Fleet Step | P2 - Medium | Animation | Sparkle/step burst optional | Rafal | Needed / placeholder
Reward / Item | Fleet Step | P2 - Medium | UI/Icon/Label | Item icon | Rafal + Martin | Needed / placeholder
Reward / Item | Quick Draw | P2 - Medium | 3D mesh/model | Card/charm/token mesh | Rafal | Needed / placeholder
Reward / Item | Quick Draw | P2 - Medium | Material | Card material with speed accent | Rafal | Needed / placeholder
Reward / Item | Quick Draw | P2 - Medium | Texture set | Card face texture/icon | Rafal | Needed / placeholder
Reward / Item | Quick Draw | P2 - Medium | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Quick Draw | P2 - Medium | Animation | Card flip optional | Rafal | Needed / placeholder
Reward / Item | Quick Draw | P2 - Medium | UI/Icon/Label | Item icon | Rafal + Martin | Needed / placeholder
Reward / Item | Stone Heart | P2 - Medium | 3D mesh/model | Heart/stone charm mesh or card art | Rafal | Needed / placeholder
Reward / Item | Stone Heart | P2 - Medium | Material | Stone/heart material | Rafal | Needed / placeholder
Reward / Item | Stone Heart | P2 - Medium | Texture set | Charm/card texture | Rafal | Needed / placeholder
Reward / Item | Stone Heart | P2 - Medium | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Stone Heart | P2 - Medium | Animation | Pickup sparkle | Rafal | Needed / placeholder
Reward / Item | Stone Heart | P2 - Medium | UI/Icon/Label | Small item icon | Rafal + Martin | Needed / placeholder
Room Designer | Inactive door anchor | P2 - Medium | 3D mesh/model | Disabled/ghosted port marker | Rafal | Needed / placeholder
Room Designer | Inactive door anchor | P2 - Medium | Material | Inactive port material | Rafal | Needed / placeholder
Room Designer | Inactive door anchor | P2 - Medium | Texture set | Disabled icon optional | Rafal | Needed / placeholder
Room Designer | Inactive door anchor | P2 - Medium | VFX | DesignerPlace/Erase | Rafal + Martin | Needed / placeholder
Room Designer | Inactive door anchor | P2 - Medium | UI/Icon/Label | doorAnchorInactive label | Rafal + Martin | Needed / placeholder
UI / HUD | Main menu root | P2 - Medium | 3D mesh/model | Menu panels/buttons/card backgrounds | Rafal | Needed / placeholder
UI / HUD | Main menu root | P2 - Medium | Material | Menu UI materials/colors | Rafal | Needed / placeholder
UI / HUD | Main menu root | P2 - Medium | Texture set | Logo/background/profile icons | Rafal | Needed / placeholder
UI / HUD | Main menu root | P2 - Medium | VFX | Button click/transition later | Rafal + Martin | Needed / placeholder
UI / HUD | Main menu root | P2 - Medium | Animation | Panel transition optional | Rafal | Needed / placeholder
UI / HUD | Main menu root | P2 - Medium | UI/Icon/Label | New Run, Continue, Challenges, Room Designer, Settings | Rafal + Martin | Needed / placeholder
UI / HUD | Profile slot card | P2 - Medium | 3D mesh/model | Card/panel UI shape | Rafal | Needed / placeholder
UI / HUD | Profile slot card | P2 - Medium | Material | Profile card material/style | Rafal | Needed / placeholder
UI / HUD | Profile slot card | P2 - Medium | Texture set | Profile icon/progress icons | Rafal | Needed / placeholder
UI / HUD | Profile slot card | P2 - Medium | VFX | Select cue later | Rafal + Martin | Needed / placeholder
UI / HUD | Profile slot card | P2 - Medium | Animation | Hover/select optional | Rafal | Needed / placeholder
UI / HUD | Profile slot card | P2 - Medium | UI/Icon/Label | Slot name, runs, banked souls, active run | Rafal + Martin | Needed / placeholder
VFX | Room clear VFX | P2 - Medium | 3D mesh/model | Room-level burst/banner | Rafal | Needed / placeholder
VFX | Room clear VFX | P2 - Medium | Material | Clear material | Rafal | Needed / placeholder
VFX | Room clear VFX | P2 - Medium | Texture set | Spark/ring texture | Rafal | Needed / placeholder
VFX | Room clear VFX | P2 - Medium | VFX | RoomClear | Rafal + Martin | Needed / placeholder
VFX | Room clear VFX | P2 - Medium | Animation | Pulse across doors/reward | Rafal | Needed / placeholder
VFX | Room clear VFX | P2 - Medium | UI/Icon/Label | Room Clear text | Rafal + Martin | Needed / placeholder
Environment | Origin marker / center floor mark | P3 - Low | 3D mesh/model | Small floor decal/ring mesh | Rafal | Needed / placeholder
Environment | Origin marker / center floor mark | P3 - Low | Material | Origin marker material | Rafal | Needed / placeholder
Environment | Origin marker / center floor mark | P3 - Low | Texture set | Decal/icon texture optional | Rafal | Needed / placeholder
Environment | Origin marker / center floor mark | P3 - Low | UI/Icon/Label | Label/debug optional | Rafal + Martin | Needed / placeholder
Environment | Spike / hazard tile | P3 - Planned | 3D mesh/model | Spike/trap mesh | Rafal | Needed / placeholder
Environment | Spike / hazard tile | P3 - Planned | Material | Hazard metal/bone material | Rafal | Needed / placeholder
Environment | Spike / hazard tile | P3 - Planned | Texture set | Hazard icon/texture | Rafal | Needed / placeholder
Environment | Spike / hazard tile | P3 - Planned | VFX | Trigger warning VFX later | Rafal + Martin | Needed / placeholder
Environment | Spike / hazard tile | P3 - Planned | Animation | Spike pulse/extend optional | Rafal | Needed / placeholder
Environment | Spike / hazard tile | P3 - Planned | UI/Icon/Label | Hazard icon | Rafal + Martin | Needed / placeholder
Reward / Item | Heavy Spark | P3 - Low | 3D mesh/model | Dense spark/weight charm | Rafal | Needed / placeholder
Reward / Item | Heavy Spark | P3 - Low | Material | Heavy spark material | Rafal | Needed / placeholder
Reward / Item | Heavy Spark | P3 - Low | Texture set | Icon texture | Rafal | Needed / placeholder
Reward / Item | Heavy Spark | P3 - Low | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Heavy Spark | P3 - Low | Animation | Spark pulse optional | Rafal | Needed / placeholder
Reward / Item | Heavy Spark | P3 - Low | UI/Icon/Label | Item icon | Rafal + Martin | Needed / placeholder
Reward / Item | Swift Charge | P3 - Low | 3D mesh/model | Card/token mesh | Rafal | Needed / placeholder
Reward / Item | Swift Charge | P3 - Low | Material | Swift/charge material | Rafal | Needed / placeholder
Reward / Item | Swift Charge | P3 - Low | Texture set | Card icon texture | Rafal | Needed / placeholder
Reward / Item | Swift Charge | P3 - Low | VFX | RewardClaim | Rafal + Martin | Needed / placeholder
Reward / Item | Swift Charge | P3 - Low | Animation | Card flip optional | Rafal | Needed / placeholder
Reward / Item | Swift Charge | P3 - Low | UI/Icon/Label | Item icon | Rafal + Martin | Needed / placeholder
VFX | Designer place/erase VFX | P3 - Low | 3D mesh/model | Small placement/erase particles | Rafal | Needed / placeholder
VFX | Designer place/erase VFX | P3 - Low | Material | Designer VFX material | Rafal | Needed / placeholder
VFX | Designer place/erase VFX | P3 - Low | Texture set | Small square/spark texture | Rafal | Needed / placeholder
VFX | Designer place/erase VFX | P3 - Low | VFX | DesignerPlace, DesignerErase | Rafal + Martin | Needed / placeholder
VFX | Designer place/erase VFX | P3 - Low | Animation | Short UI feedback | Rafal | Needed / placeholder

## VFX Audio Cues
VFX And Audio Cue Inventory
Cue-level list for visible feedback moments and related sound placeholders.
Cue | Type | Visible Use | Required Assets
ProjectileFire | VFX + Audio | Player/enemy projectile fire | Particle burst/trail, fire/projectile SFX
EnemyHit | VFX + Audio | Enemy damage feedback | Hit spark/flash, hit SFX
EnemyDeath | VFX + Audio | Enemy death/removal | Death poof/burst, death SFX
PlayerHit | VFX + Audio | Player damage feedback | Player flash/burst, player hit SFX
RewardClaim | VFX + Audio | Reward/shop pickup | Sparkle/beam, reward SFX
DoorUnlock | VFX + Audio | Door unlock/active | Rune flash/pulse, unlock SFX
RoomClear | VFX + Audio | All enemies defeated | Room clear pulse/banner, clear SFX
PortalComplete | VFX + Audio | Hub/next branch portal | Portal swirl/transition, portal SFX
DesignerPlace | VFX + Audio | Room Designer placement | Small placement particle, click/place SFX
DesignerErase | VFX + Audio | Room Designer erase | Small erase particle, erase SFX

## Naming Conventions
Naming And Intake Conventions
Recommended naming for asset drops and runtime-approved ArtPass prefabs.
Asset type | Pattern | Example | Notes
Runtime visual prefab | AP_<RoleName>.prefab | AP_EnemyNormal.prefab | Final visual-only wrapper under Assets/_Hollow/Prefabs/ArtPass/.
VFX prefab | VFX_<CueRole>.prefab | VFX_VfxEnemyHit.prefab | Visual effect prefab under ArtPass/VFX/.
Material | MAT_<Group>_<Name>.mat | MAT_Enemy_Charger.mat | Use clear group/name; keep prototype fallback separate.
Texture | TEX_<Group>_<Name>_<Map>.png | TEX_Rock_Block_Normal.png | Use map suffix: BaseColor, Normal, Roughness, Emissive, Mask.
Raw model | SRC_<Group>_<Name>.blend/fbx | SRC_Enemy_StoneWarden.blend | Raw source under Assets/_Hollow/Art/Models/... before prefab wrapping.
Room Designer marker | spawn_point_<kind> | spawn_point_enemy_turret | Semantic marker names should stay runtime-friendly.
Door anchor | doorAnchor<State>_<direction>_<lane> | doorAnchorActive_north_0 | Keep direction/lane visible for macro-room authoring.